## Risk Register
ID | Area | Risk Description | Impact | Probability | Severity | Owner | Mitigation | Status
R-01 | Architecture | Late architectural decision for feature X | High | Medium | High | TPM | Schedule decision review earlier | Open
R-02 | IP | Vendor third‑party IP delivery risk | High | High | High | TPM + Vendor Manager | Weekly vendor syncs | Mitigating
R-03 | Verification | Coverage below G3 target | High | Medium | High | Verification Lead | Increase testing depth | Open
R-04 | Timing | Timing closure risk at target frequency | Critical | Medium | High | Physical Design Lead | Early timing analysis | Watching